## Sheet1
Issue | Discription | Solution | Programer | Notes
Small cursor displaying on spash screen | See image | I have set the slider as not active in the editor & commented out the call to the slider in the LoadHelper Class | Col | I can see the method in the LoadHelper class to have the slider as an progress bar. The problem is the spash screen loads so fast it just looks like a glitch.
The warning guests cannot submit questions is unneeded. | From the main menu the button for submit question should only be active if a user has signed in with an appropriate account |  |  | Can implement these changes - will clutter hierarchy though
fail to load/error with no connection | on initiate if the game cannot hit the server nothing happens from user perspective Minimum solution: error message to user, exit program Best solution: game loads from locally stored data |  |  | There is a catch for this. DisplayErrorModal() method - positive action retries connection, negative action quits game.
Menu scene is confusing | After login the user should be taken directly to the menu. From the menu there should be a play button. | have navigatinoDrawer load directly after login add play button to menu |  | Adjusted menu for single player specific functionality.
Asset folder _Tutorial | Inside our game folder we still have an asset folder _Tutorial, do we need this? |  |  | Have removed
back buton | users need a way to go back a scene add 'back' buttons to the GUI add background script that allows for android back button to go back scenes |  |  | Have added back button, will add android back button as well
Game needs to be more colorful | When a user hits the correct answer it should light up green When a user hits the wrong answer that button should light up red and the correct answer should light up green | added color to answer button on user selection. Added time delay so users can see it | Col
Answers need to be in random locations | The location of each answer button needs to be randomised within each question. This is vital because of how the data is retrived from the database, the correct answer will always be first | ramdomised where buttons are | col
Menu scene background is different | The patterened background should be applied to all scenes |  |  | Disagree. You'll see the button outlines if you do this and if you change the button to transparent the ripple effect doesn't show. I did implement this at first and it looked horrible.
Name above menu persisting after logout | If I log in, then log in as a guest it should have 'guest' above the menu. Instead I am seeing the user name from the first time I logged in | added a clicked bool that is checked before a user makes a selection. It is set when they make a selection and reset when the next question is shown. | col | Fixed
It is possible to make multiple answer selections | after a user makes selects an answer they need to blocked from making another selection | added a clicked bool that is checked before a user makes a selection. It is set when they make a selection and reset when the next question is shown. | Col
duplications of questions are bein shown within the same game
Can see username behind 'New Game' on menu | After log in, the username text can be partially seen behind the 'New Game' text. |  | Aaron
Lord of the Rings question has no answer buttons | Every other question but this one question has no answer buttons present. |  | Aaron