## Sheet1
RISK MANAGEMENT LOG | [8 empty] | RISK MANAGEMENT LOG |  |  |  | RISK MANAGEMENT LOG
Project Name: Let's Quiz
Project Participants: Aaron, Charnes, Collin, Michelle
ID | Current Status | Name of Risk | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
#001 | Open | Server Connection Unavailable | Medium | Low | Low | Risk if server is unavailable during gameplay the user will not be able to start a new game or continue a current one. | If server is not available then the player will not be able to update game data at the end of a round. A notification will appear saying it will try again later and the game data will temporarily be stored locally. The player will be restricted to single player gameplay in this time. | Gameplay | Hosting company will inform team members of an outage and/or if traffic is reaching its limit. | If either the user has no internet connection, the server becomes unavailable or traffic limits are reached on the server. | Mitigation | In response to an outage there is not much the team can do. We will contact the server company to try and rectify the issue as soon as possible. | If traffic limits are reached we will increase our server allowance. If the server continually crashes the team will investigate a migration to another provider.
#002 | Open | Proof of Skill | High | Low | Medium | During this early stage the team is required to prove our use of the technologies we wish to use for this project. These include PHP, Unity, C# and creating apps for Android and iOS. The risk is if we are not able to do so. | The listed technologies, PHP, Unity, C#, iOS and Android development, are required for the proposed project to be completed. A failure in any one of these areas would mean we will not meet our intended goal. | Project Architecture | None of the team members are able to come up with solutions to prove our use of the technologies. | Two weeks before assignment deadline and the proposed technologies have not yet been proven. | Mitigation | Team will prioritise the technologies that have not yet been proven and collectively attempt to come up with solutions. Bringing in necessary support from staff or online resources. | Alternatively, the scope of the project would need to be changed to only use technologies that have been proven.
#003 | Closed | Project Scope | Low | Low | Low | Project scope has not been clearly identified. Group members are currently completing tasks without a succinct project vision. | Without a common vision all team members are currently developing based on their own understanding of the project. This could lead to inconsistent work being completed among members, affecting the outcome of the project. | Project Planning, Project Management | Parts of assignments are being completed without the vision document being completed. |  | Mitigation | As part of Assignment 1. A project vision will be submitted and distributed to team members throughout its development. This will give all group members the same goal when writing their documentation. | Weekly meetings are being held to keep everyone accountable for their work. Minimising any long term effects with not having this document.
#004
#005
*note: Any additional risks that come up in iteration plan meetings must be reported to this document. Conversely, any risks that are added to this plan must be brought up in iteration plan meetings.
Note on A7: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B7: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on D7: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on E7: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on F7: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on G7: • Risk Description: This column should be populated with a description of the risk.
Note on H7: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on I7: • Risk Area: This column should be populated with the appropriate risk area.
Note on J7: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on K7: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on L7: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on M7: • Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on N7: • Contingency Plan: This column should be populated with a description of the risk contingency plan.