## Sheet1
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG |  |  |  | RISK MANAGEMENT LOG
Project Name:
Project Participants:
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
#001 | Open | Medium | Low | Low | Project requires a server to allow gameplay between devices. We are currently running with the idea of using a personal server, there is a possibility that this may not be available for the duration of the project. | A server is a requirement for the functionality of this project. | Project Architecture | Collin infroms team that server is no longer aavailable OR server cannot keep up with demand during testing. | Collin will inform team if any problems arise with the personal server. During early testing we will perform tests to prove if sever can meet our required demand. | Mitigation | Team will research a backup system. If the personal proves to be insufficient for our operations or becomes unavilabel due to other reasons we will migrate to a rented server space.
#002 | Open | High | Low | Medium | During this early stage the team is required to prove our use of the technolgies we wish to use for this project. These include PHP, Unity, C# and creating apps for Android and iOS. The risk is if we are not able to do so. | The listed technologies, PHP, Unity, C#, iOS and Android development, are required for the proposed project to be completed. A failure in any one of these areas would mean we will not meet our intended goal. | Project Architecture | None of the team members are able to come up with solutions to prove our use of the technolgies. | Two weeks before assignment deadline and the proposed technolgies have not yet been proven. | Mitigation | Team will prioritise the technolgies that have not yet been proven and collectively attempt to come up with solutions. Bringing in necessary support from staff or online resources. | Alternatively, the scope of the project woulld need to be changed to only use technolgies that have been proven.
#003 | Open | Low | Low | Low | Project scope has not been clearly identified. Group members are currently completing tasks without a succient project vision. | Wuthout a common vision all team members are currently developing based on their own understanding of the project. This could lead to inconsistant work being completed among members, affecting the outcome of the project. | Project Planning, Project Management | Parts of assignments are being completed without the vision document being completed. |  | Mitigation | As part of Assignment 1. A project vision will be submitted and distributed to team members throughout its development. This will give all group members the same goal when writing their documentation. | Weekly meetings are being held to keep eveyrone accoutable for their work. Minimising any long term effects with not having this document.
#004
#005
- Several generic and a comprehensive set of project specific risks are identified, discussed and prioritized
- Mitigation strategies are specific, a plan is in place to effect those strategies, and that plan shows up in iteration planning and reporting
*note: Any additional risks that come up in iteration plan meetings must be reported to this document. Conversly, any risks that are added to this plan must be brought up in iteration plan meetings.
Note on A7: • ID: A unique ID number used to identify the risk in the risk management log.
Note on B7: • Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
Note on C7: • Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
Note on D7: • Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue. o High: Greater than 70% probability of occurrence. o Medium: Between 30% and 70% probability of occurrence. o Low: Below 30% probability of occurrence.
Note on E7: • Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
Note on F7: • Risk Description: This column should be populated with a description of the risk.
Note on G7: • Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
Note on H7: • Risk Area: This column should be populated with the appropriate risk area.
Note on I7: • Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
Note on J7: • Triggers: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
Note on K7: Risk Response Strategy: This column should be populated with the preferred risk response strategy.
Note on L7: • ResponseStrategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
Note on M7: • Contingency Plan: This column should be populated with a description of the risk contingency plan.