## Sheet1
Issue | Discription | Solution | Programer | Notes
Small cursor displaying on spash screen | See image | I have set the slider as not active in the editor & commented out the call to the slider in the LoadHelper Class | Col | I can see the method in the LoadHelper class to have the slider as an progress bar. The problem is the spash screen loads so fast it just looks like a glitch.
The warning guests cannot submit questions is unneeded. | From the main menu the button for submit question should only be active if a user has signed in with an appropriate account
fail to load/error with no connection | on initiate if the game cannot hit the server nothing happens from user perspective Minimum solution: error message to user, exit program Best solution: game loads from locally stored data
Menu scene is confusing | After login the user should be taken directly to the menu. From the menu there should be a play button. | have navigatinoDrawer load directly after login add play button to menu
Asset folder _Tutorial | Inside our game folder we still have an asset folder _Tutorial, do we need this?
back buton | users need a way to go back a scene add 'back' buttons to the GUI add background script that allows for android back button to go back scenes
Game needs to be more colorful | When a user hits the correct answer it should light up green When a user hits the wrong answer that button should light up red and the correct answer should light up green |  | aaron
Answers need to be in random locations | The location of each answer button needs to be randomised within each question. This is vital because of how the data is retrived from the database, the correct answer will always be first |  | aaron
Menu scene background is different | The patterened background should be applied to all scenes
Name above menu persisting after logout | If I log in, then log in as a guest it should have 'guest' above the menu. Instead I am seeing the user name from the first time I logged in