## all
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1.4 | Extend Leaderbaord to include new rankings | In Progress | Aaron | 8 | 5 | 3 | 1
1.5 | Update UI to accommodate extended leaderbaord | In Progress | Aaron | 4 | 2 | 2 | 1
1.1 | Implement offline redundancy in case of no internet or server connection | Not Started | Aaron | 10 | 0 | 10 | 2
1.7 | Implement new leaderboards, questions ratings, best round. | Complete | Aaron | 8 | 9 | 0 | 2
1.8 | Link upvote/downvote buttons to PHP. | In Progress | Aaron | 3 | 5 | 0 | 2
1.8 | Link upvote/downvote buttons to PHP. | Complete | Aaron |  |  |  | 2
1.9 | UI for leaderboard to include tabs | Complete | Aaron | 5 | 6 | 0 | 2
6 | Research for iOS submission | Link 1 | Aaron | 2 | 2 | 0 | 2
1 | Implement offline redundancy in case of no internet or server connection | Complete | Aaron | 10 | 9 | 0 | 3
2 | Refine UI for leaderboard to include tabs | In Progress | Aaron | 5 | 5 | 1 | 3
7.1 | Write section of user manual assigned | Not started | Aaron | 10 | 0 | 0 | 3
1 | Implement offline redundancy in case of no internet or server connection | Complete | Aaron | 10 | 10 | 0 | 4
5 | Complete voting UAT | Not started | Aaron | 2 | 0 | 0 | 4
16 | Build Project to Xcode | Complete, yet to push. | Aaron | 3 | 3 | 0 | 4
4.1 | Complete voting UAT | Not started | Aaron | 2 | 0 | 0 | 5
6.1 | Build Project to Xcode | Complete | Aaron | 3 | 3 | 0 | 5
6.2 | Upload ios game for App Store review | Not Started | Aaron | 6 | 0 | 0 | 5
9.1 | Screenshots/recording game | Not Started | Aaron | 2 | 0 | 0 | 5
18 | Leaderboards not updating | Not Started | Aaron | 3 | 0 | 0 | 5
19 | Leaderboard tabs not working | Not Started | Aaron | 1 | 0 | 0 | 5
20 | Offline redundancy not working | Not Started | Aaron | 5 | 0 | 0 | 5
7 | Draft survey | Complete | Aaron | 2 | 0 | 0 | 4
2.2 | User manual - Play Game | In Progress | Arron | 5 | 4 | 1 | 4
4.1 | Review User manual - System requirements & install | Not started | Arron | 1 | 0 | 1 | 4
1.1 | User manual - Play game | In Progress | Arron | 5 | 4 | 1 | 5
2.4 | Review User manual - System requirements & install | Not started | Arron | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Arron | 1 | 0 | 1 | 5
2.4 | Refine UI to show all games in progress (game lobby) | Complete | Charnes | 2 | 2 | 0 | 1
2 | Refine UI to show all games in progress (game lobby) | Not started | Charnes | 5 | 2 | 3 | 2
5 | Push Notifications | Project | Charnes | 20 | 0 | 20 | 2
5 | Push Notifications | Proof of implementation | Charnes | 20 | 0 | 20 | 2
5 | Push Notifications | Research | Charnes | 20 | 0 | 20 | 2
4 | Refine UI to show all game in progress (game lobby) | Complete | Charnes | 5 | 5 | 0 | 3
6.1 | first Review of phase assessment document | complete | Charnes | 10 | 0 | 0 | 3
7.3 | Write section of user manual assigned | Not started | Charnes | 10 | 0 | 0 | 3
8 | Sign APK to allow for deployment on Google Play Store | Complete | Charnes | 2 | 2 | 0 | 3
9 | Push notifications | Complete | Charnes | 5 | 5 | 0 | 3
2 | User manual - System requirements & install | Complete | Charnes | 5 | 5 | 0 | 4
4.2 | Review User manual - Game lobby | Not started | Charnes | 1 | 0 | 1 | 4
4.5 | Review User manual - Section 4 & 5 | Complete | Charnes | 1 | 1 | 0 | 4
4.6 | Review User manual - System requirements & install | Not started | Charnes | 1 | 0 | 1 | 4
12 | Execute Multiplayer UAT | Not started | Charnes | 2 | 0 | 0 | 4
13 | UI design tidy up | Complete | Charnes | 5 | 5 | 0 | 4
14 | Code tidy up | Complete | Charnes | 5 | 5 | 0 | 4
15 | review phase thing | Not started | Charnes |  |  |  | 4
2.1 | Review User manual - Game lobby | Not started | Charnes | 1 | 0 | 1 | 5
2.3 | Review User manual - System requirements & install | Not started | Charnes | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Charnes | 1 | 0 | 1 | 5
3.2 | Review Status Phase Assessment | Not started | Charnes | 2 | 0 | 0 | 5
4.3 | Execute Multiplayer UAT | Not started | Charnes | 2 | 0 | 0 | 5
8.1 | Upadte Project Plan | Not Started | Charnes | 3 | 0 | 0 | 5
10 | Fix category pop up white space | Not Started | Charnes | 1 | 0 | 0 | 5
11 | Fix place holder pop up | Not Started | Charnes | 1 | 0 | 0 | 5
14 | Fix login error - | Not Started | Charnes | 2 | 0 | 0 | 5
15 | Game scene – the time left is not displaying | Not Started | Charnes | 1 | 0 | 0 | 5
16 | After the round has finished “attempting to submit ranking” is not clearing. | Not Started | Charnes | 1 | 0 | 0 | 5
1.1 | Create database structure to allow for multiplayer playthrough | Complete | Col | 1 | 1 | 0 | 1
1.2 | Create PHP script to allow for communication between UI and database about multiplayer session | complete | Col | 5 | 5 | 0 | 1
1.3 | Create C# script to implement multiplayer playthrough and use PHP script to update database | Complete | Col | 20 | 10 | 0 | 1
2.1 | Refine database structure to allow for simultaneous multiplayer games | Complete | Col | 1 | 0.5 | 0 | 1
2.3 | Create / refine C# script to implement simultaneous multiplayer games and use PHP script to update database | Complete | Col | 15 | 20 | 0 | 1
1.3 | Create PHP script to send upvote/downvote for individual question to database. | Downvote.php | Col | 1 | 0.5 | 0 | 2
1.3 | Create PHP script to send upvote/downvote for individual question to database. | Upvote.php | Col |  | 0.5 | 0 | 2
1.4 | Add numberOfQuestionsSubmitted to Leaderboard JSON pull. | complete | Col | 1 | 1 | 0 | 2
1.5 | Research for Java JDK build issues | Complete | Col | 1 | 5 | 0 | 2
3 | Complete category implementation | complete | Col | 10 | 15 | 5 | 3
6 | Write phase assessment document | complete | Col | 10 | 2 | 8 | 3
7.2 | Write section of user manual assigned | Not started | Col | 10 | 0 | 0 | 3
2.1 | User manual - Game lobby | Completed | Col | 5 | 5 | 0 | 4
2.3 | User manual - Trouble shoot | In progress | Col | 2 | 5 | 2 | 4
4.3 | Review User manual - Play game | completed | Col | 1 | 1 | 0 | 4
6 | Fix null error button throws when clicked too early | In progress | Col | 1 | 0 | 0 | 4
8 | Category UAT |  | Col | 2 | 1 | 0 | 4
9 | Upload Game to Play store | completed | Col | 1 | 5 | 0 | 4
10 | Review survey | Not started | Col | 1 | 0 | 0 | 4
11 | Write push notification test | Completed | Col | 3 | 2 | 0 | 4
1.2 | User manual - Trouble shoot | In progress | Col | 2 | 5 | 2 | 5
3.2 | Complete Status Phase | Not Started | Col | 3 | 0 | 0 | 5
4.2 | Category UAT | Not Started | Col | 2 | 1 | 0 | 5
5.1 | Review survey | completed | Col | 1 | 0 |  | 5
7.1 | Fix null error button throws when clicked too early | In progress | Col | 1 | 0 | 0 | 5
9.1 | Screenshots/recording game | Not Started | Col | 2 | 0 | 0 | 5
12 | Fix gamelobby buttons | Not Started | Col | 1 | 0 | 0 | 5
17 | Remove text from the bottom of the spash screen | Not Started | Col | 0.25 | 0 | 0 | 5
21 | Fix intermittent fault where ongoing games not presenting | Not Started | Col | 2 | 0 | 0 | 5
22 | Disable ‘share’ button if not logged in to facebook | Not Started | Col | 1 | 0 | 0 | 5
23 | Fix category dropdown to allow users to select ‘starwars’ | Not Started | Col | 1 | 0 | 0 | 5
7 | Divide sections of user manual to team members | Complete | Michele | 1 | 0 | 0 | 3
4.2 | Is the database correctly storing current games? | In progress | Michelle |  |  |  | 1
4.3 | Is the database correctly storing each game and round progress? | In progress | Michelle |  |  |  | 1
4.4 | Is the UI being updated correctly to show each game and round progress? | In progress | Michelle |  |  |  | 1
4.5 | Is the UI showing the statues of each game correctly? | In progress | Michelle |  |  |  | 1
4.6 | Is the UI showing the user and opponent turn status correctly? | In progress | Michelle |  |  |  | 1
3.7 | Can a player vote on questions? | Completed | Michelle | 1 | 1 | 0 | 2
3.8 | Does the database store likes and dislike date correctly? | Completed | Michelle | 1 | 1 | 0 | 2
3.9 | Can the user display the voting leader board? | Completed | Michelle | 1 | 1 | 0 | 2
3.1 | Can a player choose a category | Completed | Michelle | 1 | 1 | 0 | 2
3.11 | Can a player see the category of an open game at start of round | Completed | Michelle | 1 | 1 | 0 | 2
4 | Implement Facebook Log in | In progress scripts written and buttons connected | Michelle | 10 | 20 | 10 | 2
4.1 | Implement Google Log in | In progress | Michelle | 10 | 10 | 5 | 2
5 | Complete social media integration | Fb In Progress | Michelle | 5 | 1.5 | 2 | 3
5 | Complete social media integration | GPS in Progress | Michelle | 5 | 1.5 | 2 | 3
2.4 | User manual - Section 4 & 5 | In Progress | Michelle | 5 | 0 | 5 | 4
4.4 | Review User manual - Trouble shoot | Not started | Michelle | 1 | 0 | 1 | 4
17 | Facebook Integration | Complete | Michelle | 15 | 15 | 0 | 4
18 | Wrote Facebook UATs | Complete | Michelle | 1 | 1 | 0 | 4
19 | Execute Facebook UATs | Complete | Michelle | 3 | 3 | 0 | 4
1.3 | User manual - Section 4 & 5 | In Progress | Michelle | 5 | 0 | 5 | 5
2.2 | Review User manual - Trouble shoot | Not started | Michelle | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Michelle | 1 | 0 | 1 | 5
13 | Fix facebook not loggin in | Not Started | Michelle | 3 | 0 | 0 | 5
3.1 | Can two users play against each other | In progress | Michelle |  |  |  | 1
3.2 | Is the database correctly storing open games? | In progress | Michelle |  |  |  | 1
3.3 | Is the database correctly storing game and round progress? | In progress | Michelle |  |  |  | 1
3.4 | Is the UI being updated correctly to show game and round progress? | In progress | Michelle |  |  |  | 1
3.5 | Is the UI showing the user and opponent turn status correctly? | In progress | Michelle |  |  |  | 1
4.1 | Can more than one game be opened/played? | In progress | Michelle |  |  |  | 1
3.1 | Can two users play against each other | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.2 | Is the database correctly storing open games? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.3 | Is the database correctly storing game and round progress? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.4 | Is the UI being updated correctly to show game and round progress? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.5 | Is the UI showing the user and opponent turn status correctly? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.6 | Can more than one game be opened/played? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
4
| Login screen presents weird line when text input is selected | [5 empty] | 5

## interation1
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1.1 | Create database structure to allow for multiplayer playthrough | Complete | Col | 1 | 1 | 0 | 1
1.2 | Create PHP script to allow for communication between UI and database about multiplayer session | complete | Col | 5 | 5 | 0 | 1
1.3 | Create C# script to implement multiplayer playthrough and use PHP script to update database | Complete | Col | 20 | 10 | 0 | 1
1.4 | Extend Leaderbaord to include new rankings | In Progress | Aaron | 8 | 5 | 3 | 1
1.5 | Update UI to accommodate extended leaderbaord | In Progress | Aaron | 4 | 2 | 2 | 1
2.1 | Refine database structure to allow for simultaneous multiplayer games | Complete | Col | 1 | 0.5 | 0 | 1
2.3 | Create / refine C# script to implement simultaneous multiplayer games and use PHP script to update database | Complete | Col | 15 | 20 | 0 | 1
2.4 | Refine UI to show all games in progress (game lobby) | Complete | Charnes | 2 | 2 | 0 | 1
3.1 | Can two users play against each other | In progress | Michelle |  |  |  | 1
3.2 | Is the database correctly storing open games? | In progress | Michelle |  |  |  | 1
3.3 | Is the database correctly storing game and round progress? | In progress | Michelle |  |  |  | 1
3.4 | Is the UI being updated correctly to show game and round progress? | In progress | Michelle |  |  |  | 1
3.5 | Is the UI showing the user and opponent turn status correctly? | In progress | Michelle |  |  |  | 1
4.1 | Can more than one game be opened/played? | In progress | Michelle |  |  |  | 1
4.2 | Is the database correctly storing current games? | In progress | Michelle |  |  |  | 1
4.3 | Is the database correctly storing each game and round progress? | In progress | Michelle |  |  |  | 1
4.4 | Is the UI being updated correctly to show each game and round progress? | In progress | Michelle |  |  |  | 1
4.5 | Is the UI showing the statues of each game correctly? | In progress | Michelle |  |  |  | 1
4.6 | Is the UI showing the user and opponent turn status correctly? | In progress | Michelle |  |  |  | 1

## iteration2
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1.1 | Implement offline redundancy in case of no internet or server connection | Not Started | Aaron | 10 | 0 | 10 | 2
1.3 | Create PHP script to send upvote/downvote for individual question to database. | Downvote.php | Col | 1 | 0.5 | 0 | 2
1.3 | Create PHP script to send upvote/downvote for individual question to database. | Upvote.php | Col |  | 0.5 | 0 | 2
1.4 | Add numberOfQuestionsSubmitted to Leaderboard JSON pull. | complete | Col | 1 | 1 | 0 | 2
1.5 | Research for Java JDK build issues | Complete | Col | 1 | 5 | 0 | 2
1.7 | Implement new leaderboards, questions ratings, best round. | Complete | Aaron | 8 | 9 | 0 | 2
1.8 | Link upvote/downvote buttons to PHP. | In Progress | Aaron | 3 | 5 | 0 | 2
1.8 | Link upvote/downvote buttons to PHP. | Complete | Aaron |  |  |  | 2
1.9 | UI for leaderboard to include tabs | Complete | Aaron | 5 | 6 | 0 | 2
2 | Refine UI to show all games in progress (game lobby) | Not started | Charnes | 5 | 2 | 3 | 2
3.1 | Can two users play against each other | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.2 | Is the database correctly storing open games? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.3 | Is the database correctly storing game and round progress? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.4 | Is the UI being updated correctly to show game and round progress? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.5 | Is the UI showing the user and opponent turn status correctly? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.6 | Can more than one game be opened/played? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.7 | Can a player vote on questions? | Completed | Michelle | 1 | 1 | 0 | 2
3.8 | Does the database store likes and dislike date correctly? | Completed | Michelle | 1 | 1 | 0 | 2
3.9 | Can the user display the voting leader board? | Completed | Michelle | 1 | 1 | 0 | 2
3.1 | Can a player choose a category | Completed | Michelle | 1 | 1 | 0 | 2
3.11 | Can a player see the category of an open game at start of round | Completed | Michelle | 1 | 1 | 0 | 2
4 | Implement Facebook Log in | In progress scripts written and buttons connected | Michelle | 10 | 20 | 10 | 2
4.1 | Implement Google Log in | In progress | Michelle | 10 | 10 | 5 | 2
5 | Push Notifications | Project | Charnes | 20 | 0 | 20 | 2
5 | Push Notifications | Proof of implementation | Charnes | 20 | 0 | 20 | 2
5 | Push Notifications | Research | Charnes | 20 | 0 | 20 | 2
6 | Research for iOS submission | Link 1 | Aaron | 2 | 2 | 0 | 2

## itearation 3
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1 | Implement offline redundancy in case of no internet or server connection | Complete | Aaron | 10 | 9 | 0 | 3
2 | Refine UI for leaderboard to include tabs | In Progress | Aaron | 5 | 5 | 1 | 3
3 | Complete category implementation | complete | Col | 10 | 15 | 5 | 3
4 | Refine UI to show all game in progress (game lobby) | Complete | Charnes | 5 | 5 | 0 | 3
5 | Complete social media integration | Fb In Progress | Michelle | 5 | 1.5 | 2 | 3
5 | Complete social media integration | GPS in Progress | Michelle | 5 | 1.5 | 2 | 3
6 | Write phase assessment document | complete | Col | 10 | 2 | 8 | 3
6.1 | first Review of phase assessment document | complete | Charnes | 10 | 0 | 0 | 3
7 | Divide sections of user manual to team members | Complete | Michele | 1 | 0 | 0 | 3
7.1 | Write section of user manual assigned | Not started | Aaron | 10 | 0 | 0 | 3
7.2 | Write section of user manual assigned | Not started | Col | 10 | 0 | 0 | 3
7.3 | Write section of user manual assigned | Not started | Charnes | 10 | 0 | 0 | 3
8 | Sign APK to allow for deployment on Google Play Store | Complete | Charnes | 2 | 2 | 0 | 3
9 | Push notifications | Complete | Charnes | 5 | 5 | 0 | 3

## iteration 4
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1 | Implement offline redundancy in case of no internet or server connection | Complete | Aaron | 10 | 10 | 0 | 4
2 | User manual - System requirements & install | Complete | Charnes | 5 | 5 | 0 | 4
2.1 | User manual - Game lobby | Completed | Col | 5 | 5 | 0 | 4
2.2 | User manual - Play Game | In Progress | Arron | 5 | 4 | 1 | 4
2.3 | User manual - Trouble shoot | In progress | Col | 2 | 5 | 2 | 4
2.4 | User manual - Section 4 & 5 | In Progress | Michelle | 5 | 0 | 5 | 4
4.1 | Review User manual - System requirements & install | Not started | Arron | 1 | 0 | 1 | 4
4.2 | Review User manual - Game lobby | Not started | Charnes | 1 | 0 | 1 | 4
4.3 | Review User manual - Play game | completed | Col | 1 | 1 | 0 | 4
4.4 | Review User manual - Trouble shoot | Not started | Michelle | 1 | 0 | 1 | 4
4.5 | Review User manual - Section 4 & 5 | Complete | Charnes | 1 | 1 | 0 | 4
4.6 | Review User manual - System requirements & install | Not started | Charnes | 1 | 0 | 1 | 4
5 | Complete voting UAT | Not started | Aaron | 2 | 0 | 0 | 4
6 | Fix null error button throws when clicked too early | In progress | Col | 1 | 0 | 0 | 4
4
7 | Draft survey | Complete | Aaron | 2 | 0 | 0 | 4
8 | Category UAT |  | Col | 2 | 1 | 0 | 4
9 | Upload Game to Play store | completed | Col | 1 | 5 | 0 | 4
10 | Review survey | Not started | Col | 1 | 0 | 0 | 4
11 | Write push notification test | Completed | Col | 3 | 2 | 0 | 4
12 | Execute Multiplayer UAT | Not started | Charnes | 2 | 0 | 0 | 4
13 | UI design tidy up | Complete | Charnes | 5 | 5 | 0 | 4
14 | Code tidy up | Complete | Charnes | 5 | 5 | 0 | 4
15 | review phase thing | Not started | Charnes |  |  |  | 4
16 | Build Project to Xcode | Complete, yet to push. | Aaron | 3 | 3 | 0 | 4
17 | Facebook Integration | Complete | Michelle | 15 | 15 | 0 | 4
18 | Wrote Facebook UATs | Complete | Michelle | 1 | 1 | 0 | 4
19 | Execute Facebook UATs | Complete | Michelle | 3 | 3 | 0 | 4

## iteration 5
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1.1 | User manual - Play game | In Progress | Arron | 5 | 4 | 1 | 5
1.2 | User manual - Trouble shoot | In progress | Col | 2 | 5 | 2 | 5
1.3 | User manual - Section 4 & 5 | In Progress | Michelle | 5 | 0 | 5 | 5
2.1 | Review User manual - Game lobby | Not started | Charnes | 1 | 0 | 1 | 5
2.2 | Review User manual - Trouble shoot | Not started | Michelle | 1 | 0 | 1 | 5
2.3 | Review User manual - System requirements & install | Not started | Charnes | 1 | 0 | 1 | 5
2.4 | Review User manual - System requirements & install | Not started | Arron | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Arron | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Charnes | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Michelle | 1 | 0 | 1 | 5
3.2 | Complete Status Phase | Not Started | Col | 3 | 0 | 0 | 5
3.2 | Review Status Phase Assessment | Not started | Charnes | 2 | 0 | 0 | 5
4.1 | Complete voting UAT | Not started | Aaron | 2 | 0 | 0 | 5
4.2 | Category UAT | Not Started | Col | 2 | 1 | 0 | 5
4.3 | Execute Multiplayer UAT | Not started | Charnes | 2 | 0 | 0 | 5
5.1 | Review survey | completed | Col | 1 | 0 |  | 5
6.1 | Build Project to Xcode | Complete | Aaron | 3 | 3 | 0 | 5
6.2 | Upload ios game for App Store review | Not Started | Aaron | 6 | 0 | 0 | 5
7.1 | Fix null error button throws when clicked too early | In progress | Col | 1 | 0 | 0 | 5
8.1 | Upadte Project Plan | Not Started | Charnes | 3 | 0 | 0 | 5
9.1 | Screenshots/recording game | Not Started | Aaron | 2 | 0 | 0 | 5
9.1 | Screenshots/recording game | Not Started | Col | 2 | 0 | 0 | 5
10 | Fix category pop up white space | Not Started | Charnes | 1 | 0 | 0 | 5
11 | Fix place holder pop up | Not Started | Charnes | 1 | 0 | 0 | 5
12 | Fix gamelobby buttons | Not Started | Col | 1 | 0 | 0 | 5
13 | Fix facebook not loggin in | Not Started | Michelle | 3 | 0 | 0 | 5
14 | Fix login error - | Not Started | Charnes | 2 | 0 | 0 | 5
| Login screen presents weird line when text input is selected | [5 empty] | 5
15 | Game scene – the time left is not displaying | Not Started | Charnes | 1 | 0 | 0 | 5
16 | After the round has finished “attempting to submit ranking” is not clearing. | Not Started | Charnes | 1 | 0 | 0 | 5
17 | Remove text from the bottom of the spash screen | Not Started | Col | 0.25 | 0 | 0 | 5
18 | Leaderboards not updating | Not Started | Aaron | 3 | 0 | 0 | 5
19 | Leaderboard tabs not working | Not Started | Aaron | 1 | 0 | 0 | 5
20 | Offline redundancy not working | Not Started | Aaron | 5 | 0 | 0 | 5
21 | Fix intermittent fault where ongoing games not presenting | Not Started | Col | 2 | 0 | 0 | 5
22 | Disable ‘share’ button if not logged in to facebook | Not Started | Col | 1 | 0 | 0 | 5
23 | Fix category dropdown to allow users to select ‘starwars’ | Not Started | Col | 1 | 0 | 0 | 5

## Collin
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1.1 | Create database structure to allow for multiplayer playthrough | Complete | Col | 1 | 1 | 0 | 1
1.2 | Create PHP script to allow for communication between UI and database about multiplayer session | complete | Col | 5 | 5 | 0 | 1
1.3 | Create C# script to implement multiplayer playthrough and use PHP script to update database | Complete | Col | 20 | 10 | 0 | 1
2.1 | Refine database structure to allow for simultaneous multiplayer games | Complete | Col | 1 | 0.5 | 0 | 1
2.3 | Create / refine C# script to implement simultaneous multiplayer games and use PHP script to update database | Complete | Col | 15 | 20 | 0 | 1
1.3 | Create PHP script to send upvote/downvote for individual question to database. | Downvote.php | Col | 1 | 0.5 | 0 | 2
1.3 | Create PHP script to send upvote/downvote for individual question to database. | Upvote.php | Col |  | 0.5 | 0 | 2
1.4 | Add numberOfQuestionsSubmitted to Leaderboard JSON pull. | complete | Col | 1 | 1 | 0 | 2
1.5 | Research for Java JDK build issues | Complete | Col | 1 | 5 | 0 | 2
3 | Complete category implementation | complete | Col | 10 | 15 | 5 | 3
6 | Write phase assessment document | complete | Col | 10 | 2 | 8 | 3
2.1 | User manual - Game lobby | Completed | Col | 5 | 5 | 0 | 4
2.3 | User manual - Trouble shoot | In progress | Col | 2 | 5 | 2 | 4
4.3 | Review User manual - Play game | completed | Col | 1 | 1 | 0 | 4
9 | Upload Game to Play store | completed | Col | 1 | 5 | 0 | 4
11 | Write push notification test | Completed | Col | 3 | 2 | 0 | 4
1.2 | User manual - Trouble shoot | In progress | Col | 2 | 5 | 2 | 5
3.2 | Complete Status Phase | Not Started | Col | 3 | 0 | 0 | 5 | Tomorrow
4.2 | Category UAT | Not Started | Col | 2 | 1 | 0 | 5 | Tonight
5.1 | Review survey | completed | Col | 1 | 0 |  | 5
7.1 | Fix null error button throws when clicked too early | In progress | Col | 1 | 0 | 0 | 5 | done? Test tonight
9.1 | Screenshots/recording game | Not Started | Col | 2 | 0 | 0 | 5 | Sunday
12 | Fix gamelobby buttons | Not Started | Col | 1 | 0 | 0 | 5 | Charnes
17 | Remove text from the bottom of the spash screen | Not Started | Col | 0.25 | 0 | 0 | 5 | Michelle
21 | Fix intermittent fault where ongoing games not presenting | Not Started | Col | 2 | 0 | 0 | 5 | done? Test tonight
22 | Disable ‘share’ button if not logged in to facebook | Not Started | Col | 1 | 0 | 0 | 5 | ?
23 | Fix category dropdown to allow users to select ‘starwars’ | completed | Col | 1 | 0 | 0 | 5

## Charnes
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
2.4 | Refine UI to show all games in progress (game lobby) | Complete | Charnes | 2 | 2 | 0 | 1
2 | Refine UI to show all games in progress (game lobby) | Not started | Charnes | 5 | 2 | 3 | 2
5 | Push Notifications | Project | Charnes | 20 | 0 | 20 | 2
5 | Push Notifications | Proof of implementation | Charnes | 20 | 0 | 20 | 2
5 | Push Notifications | Research | Charnes | 20 | 0 | 20 | 2
4 | Refine UI to show all game in progress (game lobby) | Complete | Charnes | 5 | 5 | 0 | 3
6.1 | first Review of phase assessment document | complete | Charnes | 10 | 0 | 0 | 3
8 | Sign APK to allow for deployment on Google Play Store | Complete | Charnes | 2 | 2 | 0 | 3
9 | Push notifications | Complete | Charnes | 5 | 5 | 0 | 3
2 | User manual - System requirements & install | Complete | Charnes | 5 | 5 | 0 | 4
4.5 | Review User manual - Section 4 & 5 | Complete | Charnes | 1 | 1 | 0 | 4
13 | UI design tidy up | Complete | Charnes | 5 | 5 | 0 | 4
14 | Code tidy up | Complete | Charnes | 5 | 5 | 0 | 4
2.1 | Review User manual - Game lobby | Not started | Charnes | 1 | 0 | 1 | 5
2.3 | Review User manual - System requirements & install | Not started | Charnes | 1 | 0 | 1 | 5
3.2 | Review Status Phase Assessment | Not started | Charnes | 2 | 0 | 0 | 5
4.3 | Execute Multiplayer UAT | Not started | Charnes | 2 | 0 | 0 | 5
8.1 | Upadte Project Plan | Not Started | Charnes | 3 | 0 | 0 | 5
10 | Fix category pop up white space | Not Started | Charnes | 1 | 0 | 0 | 5
11 | Fix place holder pop up | Not Started | Charnes | 1 | 0 | 0 | 5
14 | Fix login error - | Not Started | Charnes | 2 | 0 | 0 | 5
15 | Game scene – the time left is not displaying | Not Started | Charnes | 1 | 0 | 0 | 5
16 | After the round has finished “attempting to submit ranking” is not clearing. | Not Started | Charnes | 1 | 0 | 0 | 5
12 | Fix gamelobby buttons | Not Started | Charnes | 1 | 0 | 0 | 5

## Aaron
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
1.4 | Extend Leaderbaord to include new rankings | In Progress | Aaron | 8 | 5 | 3 | 1
1.5 | Update UI to accommodate extended leaderbaord | In Progress | Aaron | 4 | 2 | 2 | 1
1.7 | Implement new leaderboards, questions ratings, best round. | Complete | Aaron | 8 | 9 | 0 | 2
1.8 | Link upvote/downvote buttons to PHP. | Complete | Aaron |  |  |  | 2
1.9 | UI for leaderboard to include tabs | Complete | Aaron | 5 | 6 | 0 | 2
1.8 | Link upvote/downvote buttons to PHP. | In Progress | Aaron | 3 | 5 | 0 | 2
6 | Research for iOS submission | Link 1 | Aaron | 2 | 2 | 0 | 2
1 | Implement offline redundancy in case of no internet or server connection | Complete | Aaron | 10 | 9 | 0 | 3
2 | Refine UI for leaderboard to include tabs | In Progress | Aaron | 5 | 5 | 1 | 3
1 | Implement offline redundancy in case of no internet or server connection | Complete | Aaron | 10 | 10 | 0 | 4
7 | Draft survey | Complete | Aaron | 2 | 0 | 0 | 4
16 | Build Project to Xcode | Complete, yet to push. | Aaron | 3 | 3 | 0 | 4
2.2 | User manual - Play Game | In Progress | Arron | 5 | 4 | 1 | 4
6.1 | Build Project to Xcode | Complete | Aaron | 3 | 3 | 0 | 5
1.1 | User manual - Play game | In Progress | Arron | 5 | 4 | 1 | 5
4.1 | Complete voting UAT | Not started | Aaron | 2 | 0 | 0 | 5
6.2 | Upload ios game for App Store review | Not Started | Aaron | 6 | 0 | 0 | 5
9.1 | Screenshots/recording game | Not Started | Aaron | 2 | 0 | 0 | 5
18 | Leaderboards not updating | Not Started | Aaron | 3 | 0 | 0 | 5
19 | Leaderboard tabs not working | Not Started | Aaron | 1 | 0 | 0 | 5
20 | Offline redundancy not working | Not Started | Aaron | 5 | 0 | 0 | 5
2.4 | Review User manual - System requirements & install | Not started | Arron | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Arron | 1 | 0 | 1 | 5
67

## Michelle
Work Item ID | Name or key words of description | State | Assigned to (name) | Estimated Hours | Hours worked | Estimate of hours remaining | Iteration
4.2 | Is the database correctly storing current games? | In progress | Michelle |  |  |  | 1
4.3 | Is the database correctly storing each game and round progress? | In progress | Michelle |  |  |  | 1
4.4 | Is the UI being updated correctly to show each game and round progress? | In progress | Michelle |  |  |  | 1
4.5 | Is the UI showing the statues of each game correctly? | In progress | Michelle |  |  |  | 1
4.6 | Is the UI showing the user and opponent turn status correctly? | In progress | Michelle |  |  |  | 1
3.1 | Can two users play against each other | In progress | Michelle |  |  |  | 1
3.2 | Is the database correctly storing open games? | In progress | Michelle |  |  |  | 1
3.3 | Is the database correctly storing game and round progress? | In progress | Michelle |  |  |  | 1
3.4 | Is the UI being updated correctly to show game and round progress? | In progress | Michelle |  |  |  | 1
3.5 | Is the UI showing the user and opponent turn status correctly? | In progress | Michelle |  |  |  | 1
4.1 | Can more than one game be opened/played? | In progress | Michelle |  |  |  | 1
3.7 | Can a player vote on questions? | Completed | Michelle | 1 | 1 | 0 | 2
3.8 | Does the database store likes and dislike date correctly? | Completed | Michelle | 1 | 1 | 0 | 2
3.9 | Can the user display the voting leader board? | Completed | Michelle | 1 | 1 | 0 | 2
3.1 | Can a player choose a category | Completed | Michelle | 1 | 1 | 0 | 2
3.11 | Can a player see the category of an open game at start of round | Completed | Michelle | 1 | 1 | 0 | 2
4 | Implement Facebook Log in | In progress scripts written and buttons connected | Michelle | 10 | 20 | 10 | 2
4.1 | Implement Google Log in | In progress | Michelle | 10 | 10 | 5 | 2
3.1 | Can two users play against each other | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.2 | Is the database correctly storing open games? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.3 | Is the database correctly storing game and round progress? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.4 | Is the UI being updated correctly to show game and round progress? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.5 | Is the UI showing the user and opponent turn status correctly? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
3.6 | Can more than one game be opened/played? | In Progress | Michelle | 1 | 0.5 | 0.5 | 2
7 | Divide sections of user manual to team members | Complete | Michele | 1 | 0 | 0 | 3
5 | Complete social media integration | Fb In Progress | Michelle | 5 | 1.5 | 2 | 3
5 | Complete social media integration | GPS in Progress | Michelle | 5 | 1.5 | 2 | 3
2.4 | User manual - Section 4 & 5 | In Progress | Michelle | 5 | 0 | 5 | 4
4.4 | Review User manual - Trouble shoot | Not started | Michelle | 1 | 0 | 1 | 4
17 | Facebook Integration | Complete | Michelle | 15 | 15 | 0 | 4
18 | Wrote Facebook UATs | Complete | Michelle | 1 | 1 | 0 | 4
19 | Execute Facebook UATs | Complete | Michelle | 3 | 3 | 0 | 4
4
1.3 | User manual - Section 4 & 5 | In Progress | Michelle | 5 | 0 | 5 | 5
2.2 | Review User manual - Trouble shoot | Not started | Michelle | 1 | 0 | 1 | 5
3.1 | All team members to fill out relevant section of Status Phase Assessment | Not started | Michelle | 1 | 0 | 1 | 5
13 | Fix facebook not loggin in | Not Started | Michelle | 3 | 0 | 0 | 5
| Login screen presents weird line when text input is selected | [5 empty] | 5