## Sheet1
Bugs |  |  |  |  | Reports
Bug Reported | Description | Number of Reports | Developer Notes | Status
Logout cant log back in | If a user logged out, they could see all fields on the log in screen, none of them worked | 1 (001) | Confirmed by Developer | Working | No of Reports: 5
Leaderboard refresh | User had to quit app and restart for leaderbaords to update | 1 (001) | Not a bug, feature request.
No push notifications | Users reported not receving any push notificaitons during testing | 4 (001, 002, 003, 004) | Confirmed by Developer | Working | Breakdown:
Cant login with Facebook | User could not log in using Facebook | 1 (002) | Confirmed by Developer | Working | Device: 5 Android
Marvel spelt wrong | Category 'Marvel' is spelt wrong | 2 (002, 005) | Confirmed by Developer | Working | Gender: 3 male, 2 female
Submit Question inputs | Cannot edit the submit question inputs if you click off the input then click back to it. Also text not appearing on onscreen keyboard, just a line |  |  |  | Age: 19, 19, 25, 30, 32
Averages:
Desgin: 6
User Experience: 7
Enjoyment 7.5
Login: 5.5
question Submission: 6.5
gameScene: 6.5
Results: 7.5
Leaderboards: 6.5
Question Submission: 6.5
Push Notifications: 4
Non Bugs
Report | Description | Number of Reports | Developer Notes | Status
Lag at end of round | User reported a few seconds of lag at end of each round | 1 (001)
White in Lobby | User did not know what white meant in the Game Lobby | 1 (001) | Confirmed bug | Working
More feedback in result screen | User asks for more types of feedback in results screen, how many questions they get right or wrong. | 2 (001, 005) |  | Working
User could not understand Game Lobby | user was confused as to what each colour meant | 2 (002, 005)
long questions | User spent too much time reading questions rather than answering them | 4 (002, 003, 004, 005) |  | Working
Back button login | No back button on login screen | 1 (004) |  | Working
Question Submission | User not sure if there question was received | 1 (004)
Add a Miscellanious category |  | 1 (005)